## Product Backlog
Product Backlog | [14 empty] | Priority Key | Story Points Key
Project: | [14 empty] | 1 - mandatory; High | Each Theme - 25 points
Team: | [14 empty] | 2 - mandatory; medium
3 - mandatory; low
Identifier | Theme | Developer Story | As a/an | I want to | so that | User Story(corresponding to developer story) | As a/an | I want to | so that | Notes | Priority | Story Points | Sprint Assigned | Status
Status Key
DU1 | UI Skeleton | Home menu creation | UI/UX Designer | Create a hierarchical generalised menu | it can be easily updated and maintained | Responsive home menu | User | Use a responsive and clean home menu | The site navigation is easy |  | 1 | 12 | 1 | In Progress | Not Started
DU2 |  | Content sections |  | Create neatly stacked content section | The user experience is not complicated | Seamless content view |  | View neatly arranged content sections | The user experience is not complicated | The text should be aligned perfectly | 1 | 8 | 2 | Not Started | In Progress
DU3 |  | UI element’s Id and class standardisation |  | Identify tags with standard id and class names for better control | The front end architect can easily use it to make the product more responsive |  |  |  |  | The id and class names should be short and meaningful | 3 | 5 | 2 | Not Started | Completed
DS1 | Entry Point Security | Entry point Identification | Security Architect | Identify ui elements that can be used for an adversarial attack | The gathered information about the entry points can be used for future | Transparency in data points usage | User | Freely use the data entry points | I don’t have to worry about using any data points | Search for all text boxes and buttons | 1 | 7 | 1 | In Progress
DS2 |  | Third party JS scripts threat analysis |  | Check third party files | Untrusted code sources can be identified and removed | Threat resistant Browser independent view |  | Allow browsers to load the JS scripts without worrying about the threats | The browser need not be configured for any javascript safety | Research all the comments on the security of external JS libraries | 2 | 8 | 1 | In Progress
DS3 |  | Sql injection restriction at UI Level |  | Employ/add/modify/review code to restrict sql injection attack possibility | Entry points can not be used by adversaries to modify/extract data from database or meddle with server code easily | Resistance against adversarial Keywords |  | Use the text boxes without keywords usage restrictions | The user experience is not complicated and downgraded by keeping track of what to type and what not to type | Look for special characters | 2 | 5 | 2 | Not Started
DS4 |  | Security Testing |  | Employ standard UI security tests | The security employed can be verified | [5 empty] | 1 | 5 | 2 | Not Started
DE1 | Event response | Hover properties | System Architect | Create neat JS code to add mouse hover properties | The website becomes more dynamic and JS code is more powerful than css for various effects | Perfect cross browser/platform transition effects | User | Visibly witness the style effects if they are added | The user experience is better | Employ Jquery | 1 | 8 | 1 | In Progress
DE2 |  | On click response |  | Implement smooth and fast event response mechanism | The website is more dynamic and there’s a template for changing/adding code for events | Visible action on events if added |  | See/witness the on click response if present as a feature | The functionalities is used seamlessly | Use class and Id of tags to control it | 2 | 10 | 2 | Not Started
DE3 |  | Event response testing |  | Employ standard event testing mechanism | The event response can be verified | [5 empty] | 2 | 7 | 2 | Not Started
DC1 | Cross Device UI | Bootstrap Integration | Frontend Architect | Add bootstrap code files in the project | The styling and effects can be added without redundant code creation | Cross browser view uniformity | Frontend Architect | View the same style effects on all major browsers | The viewing experience is not limited by application | Check for latest as well as stable versions of code | 1 | 12 | 1 | In Progress
DC2 |  | CSS standardisation |  | Create a standard for text and picture attributes and use it | There’s uniformity in the UI/UX component which makes the content more readable | Cross device view uniformity |  | View the website uniformly on desktop systems as well as mobile | The viewing experience is not limited by device which in turn improves the engagement |  | 2 | 8 | 2 | Not Started
DC3 |  | Cross platform UI display testing |  | Test the UI on major devices for mobile friendliness | The mobile friendliness of the website is verified. |  |  |  |  | Check on all popular browsers on desktop and mobile | 1 | 5 | 2 | Not Started
Note on B5: soeadmin: Group your user stories into classes (categories): ie Access Management, Workflow, Scheduling, Admin etc - whatever is appropriate to your product

## Changes
Changes
Id | Theme | Issue and Solution | Notes | Status

## Acceptance Criteria
Acceptance Criteria
Project:
Team:
Identifier | Theme | User Story | Test Case | Test Progress | Notes | Status
UU1 | UI Skeleton | Use a responsive home menu
UU2 |  | Neat, Seamless content view
US1 | Entry Point Security | Threat resistant Browser independent view
US2 |  | Resistance against adversarial Keywords
UE1 | Event response | Perfect cross browser/platform transition effects
UE2 |  | Visible action on events if added
UC1 | Cross Device UI | Cross browser view uniformity
UC2 |  | Cross device view uniformity
Note on B5: soeadmin: Group your user stories into classes (categories): ie Access Management, Workflow, Scheduling, Admin etc - whatever is appropriate to your product

## Notes on Completion
For a good outline of Product Backlogs, read https://www.atlassian.com/agile/scrum/backlogs
When reading the article, just bear in mind that Mark's approach uses ONLY the product backlog - you will be creating the product backlog as a master list, with the detail contained in the sprint backlogs
The 'Changes' tab is to track any adjustments you make to your user stories in terms of splitting between sprints or dropping of user stories. Explain why a user story has been changed in the 'Changes' tab
The 'Changes' tab would be empty for initial submission
The 'Acceptance Criteria' tab should list only your mandatory user stories. You can track your completion and your client acceptance in this sheet
For the initial submission of your Product Backlog you may only have a list of the acceptance criteria - the detailed columns can be completed as you progress